## Sheet1
ACTIVITY | TYPE | FILE_NAME | TIME
Awarded a green card 2015 revalidation result at the GGN Conference in Japan | __BY_PARK | English_Riviera_progress | 2015-09/2016-03
Main activities are focused on preparations towards hosting the 7th International Conference on Global Geoparks and associated meetings. GGN2016 website went live in Dec 15 and abstracts opened in February 16. Ongoing liaison with sponsors, venues, partners and training package under development for Geopark Ambassador volunteers. Development of pre conference English language course for delegates. | __BY_PARK | English_Riviera_progress | 2015-09/2016-03
£50,000 bid to Arts Council England to develop a community led music/theatrical performance to open the conference was successful. Artistic Director and the creative team have been appointed and liaison with all members of the GGN taken place re content. Community call for young composers (age 14 to 35) issued in Feb 16 and community workshops to commence mid Feb 16. Further call for community performers (age 8 to 80) to be issued in April. | __BY_PARK | English_Riviera_progress | 2015-09/2016-03
Further £10,000 bid to Arts Council England to support further creative community engagement in GGN2016. The project has three aspects (i) Geopark resident artist Bex Glover working with students at South Devon College to create hanging banners for the conference centre. (ii) Participatory local artists working in schools and youth settings to creat an as yet undefined piece of work to be finished by delegates during the conference. (iii) Local Charity MASH working with artists and local groups to “upcycle” old furniture for the creation of a delegates “relax and network area” at the conference (the furniture will be returned to the charity post conference and be donated to homes in need). | __BY_PARK | English_Riviera_progress | 2015-09/2016-03
PhD student engaged to evaluate the benefit of above mentioned creative projects against the conference theme of Health and Wellbeing through Creative and Active Engagement. | __BY_PARK | English_Riviera_progress | 2015-09/2016-03
New education advisory team established including South Devon College, Plymouth University, Exeter University, Torquay Girls Grammar School representing secondary level schools and Curledge St Academy representing primary level education. The team hope to establish a wealth of education activity led by higher level students delivering Geopark activities for primary schools capitalising on opportunities in light of the conference. | __BY_PARK | English_Riviera_progress | 2015-09/2016-03
Mayoral and all Councillor briefing led by Melanie Border and Nick Powe took place on 25 February 16 | __BY_PARK | English_Riviera_progress | 2015-09/2016-03
Awareness raising meeting with European Centre for Human Health based in Truro, Cornwall, October 2015 | __BY_PARK | English_Riviera_progress | 2015-09/2016-03
New seat for South Devon College established on the Geopark Management Group | __BY_PARK | English_Riviera_progress | 2015-09/2016-03
Participation of Melanie Border in the 36th European Geoparks Network Advisory Committee meeting in Rokua, Finland. | __NETWORK | English_Riviera_progress | 2015-09/2016-03
Participation of Nick Powe and Melanie Border at the 36th meeting of the European Geoparks Network Coordination Committee, in Rokua, Finland. | __NETWORK | English_Riviera_progress | 2015-09/2016-03
Participation of Melanie Border and GGN2016 Conference Director David Randall at the 13th European Geoparks Conference. | __NETWORK | English_Riviera_progress | 2015-09/2016-03
Participation of David Randall at the 4th APGN 2015 Symposium in San’in Kaigan, Japan. | __NETWORK | English_Riviera_progress | 2015-09/2016-03
Melanie Border continues to chair the UK Geopark Geoparks Forum and engaged in ongoing discussions with the UK National Commission for UNESCO in advance of the UNESCO General Conference in Nov 2015 thus supporting the decision to approve the new IGGP. | __NETWORK | English_Riviera_progress | 2015-09/2016-03
Organised remote teleconference meetings of the UK Global Geoparks Forum members in Nov 2015 to discuss approve appropriateness of two aspiring Geoparks applications for support from UKNC and onward submission. | __NETWORK | English_Riviera_progress | 2015-09/2016-03
Liaison with and support of two aspirant Geopark areas on behalf of the UKGGF. | __NETWORK | English_Riviera_progress | 2015-09/2016-03
Organisation and preparation for the two day annual meeting of the UKGGF to be hosted by Marble Arch Caves (2-3 March 16). | __NETWORK | English_Riviera_progress | 2015-09/2016-03
Meeting with Peter Chowne representing Jersey Heritage Trust who are considering potential Geopark application. | __NETWORK | English_Riviera_progress | 2015-09/2016-03
Impact and Engaged Research Network seminar day on the English Riviera UNESCO Global Geopark organised by Research and Knowledge Transfer Department at Exeter University. | __By_PARTNER | English_Riviera_progress | 2015-09/2016-03
English Riviera Tourism Company organised journalist visit for Swedish journalist group. | __By_PARTNER | English_Riviera_progress | 2015-09/2016-03
All Geopark partners are planning events for the Geopark Festival 2016. | __By_PARTNER | English_Riviera_progress | 2015-09/2016-03
Torbay Community Development Trust and Paignton Community Partnership continue to work together to ensure the sustainability of the Paignton Geoplay Park through the potential addition of refreshment kiosk to the site. | __By_PARTNER | English_Riviera_progress | 2015-09/2016-03
Promotion of the English Riviera by the Association of GeoConservation in Hong Kong at their GeoHero Run event. | __By_PARTNER | English_Riviera_progress | 2015-09/2016-03
Kents Cavern Jawbone featured in Natural History Museum of London travelling exhibition titled “Britain’s First Humans”. | __By_PARTNER | English_Riviera_progress | 2015-09/2016-03
Exeter University research on coastal erosion rates initiated Jan 16. | __By_PARTNER | English_Riviera_progress | 2015-09/2016-03