## Sheet1
ACTIVITY | TYPE | FILE_NAME | TIME
Presentations on the Geopark to partner staff and clusters, March-July. | __BY_PARK | Katla_progress | 2017-03/2017-09
Presentations and workshops with primary schools for the criteria of GeoSchools. | __BY_PARK | Katla_progress | 2017-03/2017-09
Teaching of pupils in Kirkjubæjarskóli including PowerPoint lecture, map and quiz | __BY_PARK | Katla_progress | 2017-03/2017-09
Partner contracts with Governmental agencies: National Heritage, Vatnajökull National Park and Environmental Agency. | __BY_PARK | Katla_progress | 2017-03/2017-09
Signed contract with National Government for 5 years annual funding, July. | __BY_PARK | Katla_progress | 2017-03/2017-09
Hiring of two full time geologists, May-July. | __BY_PARK | Katla_progress | 2017-03/2017-09
Partner contract with museums and centers: Skógar Heritage museum, Kötlusetur & Skaftfellingur, Vík and Kirkjubæjarstofa culture centre, May-August. | __BY_PARK | Katla_progress | 2017-03/2017-09
Two meetings including presentations an SWAT analysis of cluster Friður og frumkraftar on merging with the Geopark. | __BY_PARK | Katla_progress | 2017-03/2017-09
Individual partner contracts with 13 enterprises. | __BY_PARK | Katla_progress | 2017-03/2017-09
Primary schools Víkurskóli and Hvolsskóli accept the criteria for UNESCO GeoSchools and become GeoSchools of Katla UNESCO Global Geopark. | __BY_PARK | Katla_progress | 2017-03/2017-09
Management plan of Katla Geopark, 2 public meetings and making of questionnaire. | __BY_PARK | Katla_progress | 2017-03/2017-09
Signage for Geosites showing UGG logos as well as UGG logos on info panels. | __BY_PARK | Katla_progress | 2017-03/2017-09
Nature signs printed and erected in entire Geopark. | __BY_PARK | Katla_progress | 2017-03/2017-09
Maps of the area printed and erected in chosen locations within the territory. | __BY_PARK | Katla_progress | 2017-03/2017-09
Signed clothing for staff and partners. | __BY_PARK | Katla_progress | 2017-03/2017-09
Table flags with Katla and UGG logos for all the territory where appropriate. | __BY_PARK | Katla_progress | 2017-03/2017-09
UGG flags for schools, municipalities and non-profit partner museums. | __BY_PARK | Katla_progress | 2017-03/2017-09
Road signs showing the territory from all entrances as UNESCO Global Geopark. | __BY_PARK | Katla_progress | 2017-03/2017-09
Revalidation mission of Katla UGG, July 2017. | __BY_PARK | Katla_progress | 2017-03/2017-09
Making of GeoSaga exhibition of Katla Geopark, presented during revalidation. | __BY_PARK | Katla_progress | 2017-03/2017-09
Constant updating of fb and website. Events calendar on website. | __BY_PARK | Katla_progress | 2017-03/2017-09
New stationary for Katla UGG, folders and papers, showing UNESCO logo. | __BY_PARK | Katla_progress | 2017-03/2017-09
Updating of brochure on Katla Geopark, geosites and culture, including new map, UGG intro text and new UGG logo. | __BY_PARK | Katla_progress | 2017-03/2017-09
New flyer made and printed/distributed, including new map, nature code, nature signs, GeoSaga overview, UGG introduction and visibility, and introduction of partners. | __BY_PARK | Katla_progress | 2017-03/2017-09
Showcasing of GeoProducts of partners in Kötlusetur, Vík. | __BY_PARK | Katla_progress | 2017-03/2017-09
GeoPark corner in Kötlusetur Vík, introducing other UGGeoparks. | __BY_PARK | Katla_progress | 2017-03/2017-09
Making of new tourist map for the area, first time for the three municipalities, new informative text on 33 geosites, photos and simple geological map. In collaboration with marketing of south Iceland and the Westman islands. | __BY_PARK | Katla_progress | 2017-03/2017-09
Contract with the marketing body of south Iceland. | __BY_PARK | Katla_progress | 2017-03/2017-09
Marketing analysis of the South Iceland, Katla Geopark plays integral role. | __BY_PARK | Katla_progress | 2017-03/2017-09
Participation in the 33rd European Geoparks Network Coordination Committee meeting in Sobrarbe Geopark, Spain, March 2017. | __NETWORK | Katla_progress | 2017-03/2017-09
Publishing an article in the European Geoparks Magazine, Issue 11, March 2017. | __NETWORK | Katla_progress | 2017-03/2017-09
Organisation and promotion of the EGN Week: oral presentations, excursions, education and workshop at Skógar heritage museum, annual off-road race around geosite, popular hike and involvement of primary school. | __NETWORK | Katla_progress | 2017-03/2017-09
GeoMuseum/ GeoVR meeting (Magma, Illulusat, Jarðfeingi), Faroes June (BD). | __NETWORK | Katla_progress | 2017-03/2017-09
Drifting apart, meeting in Canada, May (SS). | __NETWORK | Katla_progress | 2017-03/2017-09
Publication of newsletter nr 3. July https://issuu.com/arnykarvelsdottir/docs/fr__ttabr__f_2__rg1tbl | __NETWORK | Katla_progress | 2017-03/2017-09
Translation and publication of UGG brochure in Icelandic, May-June. | __NETWORK | Katla_progress | 2017-03/2017-09
Co-application of RURITAGE project, as role model for heritage acting as a component for public resilience to geo-hazards. First phase approved, ongoing. | __NETWORK | Katla_progress | 2017-03/2017-09
Collecting and preparing for publishing: reports on European Geoparks Week and progress report March–September 2017, August. | __NETWORK | Katla_progress | 2017-03/2017-09
Work meeting in Scotland with Soil conservation for ASCENT project on highland paths. | __NETWORK | Katla_progress | 2017-03/2017-09
Attending meeting in Canterbury, UK on sustainable tourism, SMARTTOUR (BS). | __NETWORK | Katla_progress | 2017-03/2017-09
Work with French MS student on natural hazards and inhabitants perspective. | __NETWORK | Katla_progress | 2017-03/2017-09
Meeting in Iceland Reykjanes with Nordic Geoparks, May. | __NETWORK | Katla_progress | 2017-03/2017-09
Environmental agency increases rangers in the Geopark on protected areas. | __By_PARTNER | Katla_progress | 2017-03/2017-09
Participation of most of our formal partners in the revalidation mission 2017. | __By_PARTNER | Katla_progress | 2017-03/2017-09
Making of project on geosite “Paradísarhellir” love story, design and prototype of gold rings, Friður og frumkraftar. | __By_PARTNER | Katla_progress | 2017-03/2017-09
Opening of exhibition on Skaftfellingur, highly important merchandise ship in Vík. | __By_PARTNER | Katla_progress | 2017-03/2017-09
Opening of LAVA interactive educational centre on geology, where Katla UGG is highly visible + actual time monitoring of geo-activity and hazards, Hvolsvöllur June | __By_PARTNER | Katla_progress | 2017-03/2017-09
Opening of new video show and local handcraft/coffee house, Eyrarland, Vík, July. | __By_PARTNER | Katla_progress | 2017-03/2017-09
Application phase of ResInTour international project with European UGG, formal partner Háskólafélag Suðurlands, on Resilience and natural hazards. | __By_PARTNER | Katla_progress | 2017-03/2017-09
New tourist map of South Iceland where Katla Geopark is outlined, June. | __By_PARTNER | Katla_progress | 2017-03/2017-09