## Sheet1
ACTIVITY | TYPE | FILE_NAME | TIME
Eight geotrails redrafted and reprinted covering the whole area (Feb 2015). | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
Work continuing on new geologically focused trail to High Cup Nick (geosite) (Jan 2014). | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
New interpretation in development at our Bowlees Visitor Centre. This is touch- screen, with artefacts, fossils etc. with a digital ‘chip’ that are placed on a pad, revealing interpretation under various themes. This is an approx. 20,000 euro project which should be completed by early April. Also, using new large screens, we are turning our panels and material from our book ‘Reading the Rocks’ into interpretive materials for the centre (Jan-March 2015). | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
Completion of the next phase of our electric bike network with five further locations for hire, including our Visitor Centre (Feb 2015). | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
Continuation of work with Environment Agency and Coal Authority to develop action to reduce pollution by heavy metals from historic lead and zinc mining sites. | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
Recruitment of two further graduate trainees in conservation and land management. They will gain experience of all aspects of the work of the Geopark team (Jan 2015). | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
Review of the Geodiversity Action Plan, resulting in proposals for a shorter, simpler and more focused annual document. | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
Further development of our new three year Landscape Partnership Scheme in Allen Valleys which will provide conservation and community activities of a wide range of topics in part of the Geopark (April 2014), including new trails, restoration of heritage buildings and habitat improvements. | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
Work continues on our peatland restoration programme, including blocking drainage ditches on the moors to improve these important wetlands. | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
Work continued on our ‘Nectarworks’ project, which aims to help communities and schools to restore and increase flower-rich habitats in order to help bumblebees and other pollinators. Wild flower seed was harvested from flower- rich banks and used to seed new wild flower areas. | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
We secured funds for further work to promote dark skies and star gazing tourism. A series of winter events is being delivered and a programme is being developed for the coming year. | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
Following our research last summer on community attitudes to the development of tourism in the Geopark, (as part of work towards the EUROPARC Charter for Sustainable Tourism), a tourism business survey and a new visitor survey are being developed. | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
We are developing a Natural Capital Investment Plan for our area, and neighbouring Protected Landscapes, whilst leading on a national project to produce such plans. This is aimed at identifying and quantifying our natural capital and promoting private sector investment. | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
We have facilitated a new Farmer Forum, as part of our work on High Nature Value Farming. | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
Work continues with our neighbouring National Park to the north on our community archaeology project (the subject of a presentation to a previous EGN Conference). | __BY_PARK | North_Pennines_progress | 2014-09/2015-03
Participation in the UK Geopark Forum meeting in Geomon Geopark (March 2015). | __NETWORK | North_Pennines_progress | 2014-09/2015-03
Participation in the 34th European Geoparks Network Coordination Committee meeting in Germany in September 2014. | __NETWORK | North_Pennines_progress | 2014-09/2015-03
We received 10 delegates in our Geopark as part of the Leonardo da Vinci project ‘Geo-Education in Action’. The participants came from Beigua, Arouca and Lesvos. | __NETWORK | North_Pennines_progress | 2014-09/2015-03
We will be sending 7 delegates to the next Leonardo meeting in Portugal at the end of March | __NETWORK | North_Pennines_progress | 2014-09/2015-03
Delivery of the second North Pennines Walking Festival in October 2014. | __By_PARTNER | North_Pennines_progress | 2014-09/2015-03
Major bridge restoration by the National Trust at Allen Banks, bringing one of our Geotrails back into use. | __By_PARTNER | North_Pennines_progress | 2014-09/2015-03