## Sheet1
ACTIVITY | TYPE | FILE_NAME | TIME
We submitted a 1million Euro geodiversity-focused bid to the UK Heritage Lottery Fund but sadly we discovered in May that this was not successful. The competition for funds in the UK is intense at this time, as it may be elsewhere. The work included new geotrails, work in schools, geobike trails, writing and photography workshops, apprenticeships and international GeoYouth Camps, all on a geodiversity theme. We are now trying to reshape this work into two smaller submissions, but it will inevitably lose some of the more costly items, including the Youth Camps in which some other Geopark teams had kindly expressed interest. | __BY_PARK | North_Pennines_progress | 2016-03/2016-09
We have launched our new project – OREsome North Pennines. This project involves working with and training volunteers to record geodiversity, mining heritage and ecology of former lead mining sites, leading to a programme of future conservation work and interpretation. | __BY_PARK | North_Pennines_progress | 2016-03/2016-09
After 18 months in development we have a submitted £2million to the Heritage Lottery Fund for a landscape scale project in the North West corner of our area which will involve significant work on understanding, celebrating and exploring geological heritage in the area (which is heavily modified by glaciation as well as having an attractive limestone escarpment and small scale coal and lead mining heritage). A decision is due on 25th October. | __BY_PARK | North_Pennines_progress | 2016-03/2016-09
A long-delayed project - new interpretation touch-screen interpretation, with artefacts, fossils etc. with a digital ‘chip’ that are placed on a pad, revealing interpretation under various themes – should move forward shortly as we have dedicated one of our apprentices to complete it. | __BY_PARK | North_Pennines_progress | 2016-03/2016-09
We are continuing to develop our work alongside the Coal Authority and Environment Agency around taking action to reduce pollution by heavy metals from historic lead and zinc mining sites. | __BY_PARK | North_Pennines_progress | 2016-03/2016-09
Further development of our new three year Landscape Partnership Scheme in Allen Valleys which provides conservation and community activities of a wide range of topics in part of the Geopark, including new trails, restoration of heritage buildings and habitat improvements. | __BY_PARK | North_Pennines_progress | 2016-03/2016-09
Work continues on our peatland restoration programme, including blocking drainage ditches on the moors to improve these important wetlands. A 12m euro partnership bid to the EU LIFE fund will be submitted on 15th September to further this work, including the development of new financing models. | __BY_PARK | North_Pennines_progress | 2016-03/2016-09
We completed a tourism business survey and held our annual Tourism Seminar, attended by over 50 people from local businesses and tourism organisations. | __BY_PARK | North_Pennines_progress | 2016-03/2016-09
As part of our work on High Nature Value Farming we are part of a partnership which has secured DG Environment funding to run a pilot results-based agri- environment scheme. | __BY_PARK | North_Pennines_progress | 2016-03/2016-09
Participation in the 37th EGN Meeting in spring 2016. | __NETWORK | North_Pennines_progress | 2016-03/2016-09
A celebration was held this year for the 120th Anniversary of the Vieille Montagne Mining Zinc Company of Belgium’s arrival in the North Pennines. Miners from mainland Europe came with this company to the North Pennines in the early 20th century. The celebration involved local people and delegations from Italy, Belgium, Germany joining a Conference exploring the history of mining. They also visited the company’s former mines in the North Pennines and were shown some of the underground mine workings”. | __By_PARTNER | North_Pennines_progress | 2016-03/2016-09
.Killhope, the North of England Lead Mining Museum – an important geology and mining heritage attraction in the Geopark – is undergoing a period of financial uncertainty. The Geopark team will do all it can to help but the future of the museum is unclear. | __By_PARTNER | North_Pennines_progress | 2016-03/2016-09
A group of local people, including one of our two EGN reps Peter Jackson, is currently engaged in trying to save some historic mining heritage (and important headgear structure) from being lost from the landscape involves working with the landowner to try and find a long-term solution to site management, safety and insurance, or this iconic feature of the Rookhope Valley will be lost. | __By_PARTNER | North_Pennines_progress | 2016-03/2016-09