## Sheet1
ACTIVITY | TYPE | FILE_NAME | TIME
Revalidation Mission was held at the territory of the Novohrad–Nógrád Geopark from 26 - 29 June 2014. The received experts were Kristin Rangnes and Goran Pavic. | __BY_PARK | Novohrad-Nograd_progress | 2014-03/2014-09
We are continuously realizing our high priority, government-supported tourism development project. We almost finished building the Geopark Education, Research and Management Centre and the Geopark Visitor Center. We developed our copyrighted photo gallery, the webpage and the mobile applications are in progress. The other tasks ahead of this project: we will be opening an old mine’s entrance, furthermore we are building 7 new, and renewed 2 study trails, placing 8 welcome boards along major transport routes in the borders of the geopark; books, maps, brochures, camp assets (tents, sleeping bags, mountain bikes, etc.) etc. until the end of 2014. | __BY_PARK | Novohrad-Nograd_progress | 2014-03/2014-09
Publishing news on the EGN CC 33rd meeting in Spain in the media, on the website and Facebook. (March 2014.) | __BY_PARK | Novohrad-Nograd_progress | 2014-03/2014-09
Numerous interviews and articles on the Geopark in the national and regional media. (March–September 2014.) | __BY_PARK | Novohrad-Nograd_progress | 2014-03/2014-09
Geological educational programme for children in Somoskőújfalu, Vanyarc and in Salgótarján. (April 2014.) | __BY_PARK | Novohrad-Nograd_progress | 2014-03/2014-09
We finished discussions about joining of Vanyarc village to the geopark. The little settlement next to our geopark’s southern border is famous for its gastronomical traditions, the Kisberi horse breed and an equestrian center. (May 2014.) | __BY_PARK | Novohrad-Nograd_progress | 2014-03/2014-09
Participation and presentation in the “Green Countryside” programme (section Naturparks, Greenways and Geoparks) of the National Agricultural Consulting, Education and Rural Development Institute (Governmental Institute) in Budapest (April 2014). | __BY_PARK | Novohrad-Nograd_progress | 2014-03/2014-09
Participation in updating the strategy of the Slovakian geoparks with the Ministry of Environment in Bratislava (July, 2014.) | __BY_PARK | Novohrad-Nograd_progress | 2014-03/2014-09
Participation in the 33rd European Geoparks Network Coordination Committee meeting in Spain. (March 2014.) | __NETWORK | Novohrad-Nograd_progress | 2014-03/2014-09
Organisation and wide promotion of the EGN Week: guided tours, school activities, forums, conference, verbal presentations, signing the agreement about the minor extension of the geopark (Vanyarc settlement), and opening a geological exhibition in the village with a conference. (May–June 2014.) | __NETWORK | Novohrad-Nograd_progress | 2014-03/2014-09
Submitting an application to the Visegrad Fund about establishing the geopark’s official background with different sectors, based on good practices of the Bohemian Paradise Geopark and a Muskau Arch transboundary geopark. The application was successful, the support contract (a non-refundable grant of 12,000 EUR with 80% intensity) was signed, the project will start in September. (March-August 2014.) | __NETWORK | Novohrad-Nograd_progress | 2014-03/2014-09
Signing the grant agreement (95,911 EUR non-refundable grant, 95% intensity) of the HU-SK CBC (Hungary-Slovakia Cross-border Cooperation) project, called “Systematic partnership for the integrated development of the Novohrad–Nógrád Geopark”. The project is in synergy with the other application (see the point above). Its results will: - create the official, transboundary partnership network (with 4 sectors) of the Novohrad–Nógrád Geopark, which is also the basis for the geopark logo- using. - create 4 feasibility studies for future projects of the geopark - based on our own plans and the recommendations and requests of partnership network’s members. - refresh all of the key documents of the Novohrad–Nógrád Geopark, like Master Plan, Marketing Plan, Management and Treatment Plans, etc., - organize several workshops with the partners, and a big conference in the end, etc. (August, 2014.) | __NETWORK | Novohrad-Nograd_progress | 2014-03/2014-09
The Salgótarján Local TDM (tourist destination management) organisation developed the “Geothinks” mobile application with information about some short walks on geopark study trails. (March – September 2014.) | __By_PARTNER | Novohrad-Nograd_progress | 2014-03/2014-09
Organizing the Photographer’s Marathon in the Novohrad–Nógrád Geopark (11- 12 October) in cooperation with the Karancs–Medves Nature Conservation Foundation and the Castle Museum of Fil’akovo. This is the most important short-term event of the Novohrad–Nógrád Geopark (from March 2014). | __By_PARTNER | Novohrad-Nograd_progress | 2014-03/2014-09
Discussion with the Municipality of Salgótarján City, in connection with the planning of the city’s objectives in the 2014-2020 EU budget period (March – September 2014). | __By_PARTNER | Novohrad-Nograd_progress | 2014-03/2014-09
The Ipoly Forestry Company finished 2 new study trails (“andesite slide” of Bér, Valley of the Páris river) with the brand elements of our geopark. The Bükk National Park Directorate set up a park with specimens of endemic plants – the information panels were made with the brand elements of our geopark (Marc - May 2014). | __By_PARTNER | Novohrad-Nograd_progress | 2014-03/2014-09
Hollókő World Heritage Maintenance and the Municipality of Kalonda developed 2 new study trails from their common HU-SK CBC project, which were made with the brand elements of our geopark (Marc - May 2014). | __By_PARTNER | Novohrad-Nograd_progress | 2014-03/2014-09
From a HU-SK CBC project, two organizations started developing a more than 20 kilometres long complex tourist route along the Hungarian-Slovakian border. | __By_PARTNER | Novohrad-Nograd_progress | 2014-03/2014-09