## Sheet1
ACTIVITY | TYPE | FILE_NAME | TIME
Preparation of the Geopark enlargement: communication with representatives of proposed area, presentation of the document Enlargement of the Novohrad– Nógrád Geopark towards Hungarian Commission of UNESCO and Hungarian Geoparks Commission, preparation of new geological map (March 2017 – June 2017) | __BY_PARK | Novohrad-Nograd_progress | 2017-03/2017-09
Participation on activities of Slovak Commission of UNESCO (March 2017) | __BY_PARK | Novohrad-Nograd_progress | 2017-03/2017-09
Presentation of the Novohrad–Nógrád Geopark on the UNESCO Conference Benefits Beyond Inscription: Leveraging the UNESCO Brand for Sustainable Tourism Development held in Bardejov Spa, Slovakia (May 2017) | __BY_PARK | Novohrad-Nograd_progress | 2017-03/2017-09
Realisation of common cross-border project financed from ERASMUS Programme - Geopark Ambassadors (April – September 2017) | __BY_PARK | Novohrad-Nograd_progress | 2017-03/2017-09
Environmental education and edification (March 2017 – August 2017): a. Publication of a tourist map of the Medves Region (part of the NNG UGG) in scale of 1:33000, resp. 1:15000 (July 2017) b. 7 guided tours to the Geopark sites for general public (March 2017 – August 2017) c. “Birds and Trees Day” regional competition in Eresztvény Education, Research and Managing Centre (March 2017) d. “Hunting Quest” – special program in frame of Autism World Day in Eresztvény Education, Research and Managing Centre (April 2017) e. Photo-trip for general public (April 2017) f. Programs for visitors during Easter (hiking, games for kids) (April 2017) g. “Castles, mansions, manor-houses” – exhibition in the “House of Geo- miracles” in Salgóbánya Visitors Centre (April - May 2017); h. The European Geoparks Week in Novohrad–Nógrád Geopark - under patronage of the Slovak Commission of UNESCO (May – June 2017) a. “Volcano Day” in Nature Reserve Ipolytarnóc Fossils – various lectures for kids and volcano model presentations (May 2017) b. “Explore the Novohrad–Nógrád Geopark” – quiz, fun, competition for the kids, Fiľakovo Town park, Hajnáčka Castle (May 2017) c. “We are playing in Geopark” – teenagers prepare games for the kindergarten kids (May 2017) d. “Souvenir for Geopark” – art-competition for local primary and secondary schools (May 2017) e. “Family day” – 1 day programme for families full of activities for kids, trips guided by geologists, handicrafts activities etc., Eresztvény Education, Research and Managing Centre, Salgó Castle (June 2017) f. International Summer Camp of NNG (31st July – 4th August 2017) g. “Night in Eresztvény” – night program (hiking, bat and insect capture, guitar concert) – two events (July and August 2017) h. Cultural activities in Eresztvény Education, Research and Managing Centre (June – August 2017) i. Guided tours and lectures purchased from other subjects (schools from Salgótarján, Hungarian Catastrophe Protection, …) (march – August 2017) j. Achievement Hiking – 15-, 30- and 90-km long hiking trails in NNG UGG (September 2017) | __BY_PARK | Novohrad-Nograd_progress | 2017-03/2017-09
Re-construction of 3 educational paths in Šomoška, Mačacia and Stará Bašta (April 2017 – August 2017) | __BY_PARK | Novohrad-Nograd_progress | 2017-03/2017-09
Annual General Assemblies of the Z.p.o. Geopark Novohrad–Nógrád, Fiľakovo and the Novohrad–Nógrád Nonprofit Kft., Salgótarján (March 2017 - June 2017) | __NETWORK | Novohrad-Nograd_progress | 2017-03/2017-09
Co-operation with National Geoparks Commissions in SK and HU (meetings, consultations, conferences) (March 2017 – August 2017) | __NETWORK | Novohrad-Nograd_progress | 2017-03/2017-09
Continuous communication with other partners in Geopark (schools, expert organisations, civil societies, entrepreneurs, etc.) | __NETWORK | Novohrad-Nograd_progress | 2017-03/2017-09
Consultations with self-governments in the field of project preparation and realisation (village renewal, local development, environmental issues, ...) (March 2017 – August 2017) | __NETWORK | Novohrad-Nograd_progress | 2017-03/2017-09
Meeting of the Working Group on Nature Conservation and Landscape Protection of the Hungarian Slovak Joint Committee on Environment and Nature Conservation in Ipolytarnóc (March 2017) | __By_PARTNER | Novohrad-Nograd_progress | 2017-03/2017-09
Uncovering a memorial board of Tuzson János, researcher of the petrified tree in Ipolytarnóc | __By_PARTNER | Novohrad-Nograd_progress | 2017-03/2017-09
Helping the Slovak Mineralogy Association with the preparation and realisation of the information panel on the Sapphire occurrence in Novohrad–Nógrád Geopark | __By_PARTNER | Novohrad-Nograd_progress | 2017-03/2017-09
Participation in Danube GeoTour Project (Valorisation of geo-heritage for sustainable and innovative tourism development of Danube Geoparks) – co- operation with the project partner University of Prešov (working on the document “Overview of legislation on recreation activities affecting geo-heritage in Novohrad–Nógrád UGG”) (March – August 2017) | __By_PARTNER | Novohrad-Nograd_progress | 2017-03/2017-09
Participation on the tourism trade fair Utazás in Budapest (March 2017) | __By_PARTNER | Novohrad-Nograd_progress | 2017-03/2017-09
Presentation of NNG UGG during various events organised by other subjects for general public | __By_PARTNER | Novohrad-Nograd_progress | 2017-03/2017-09