## Sheet1
ACTIVITY | TYPE | FILE_NAME | TIME
Publishing several news on the media (TV, radio, press), off and on line. Active presence in social networks: Facebook https://www.facebook.com/geoparkodsherred/?ref=aymt_homepage_panel | __BY_PARK | Odsherred_progress | 2016-09/2017-03
Updating the web site www.geoparkodsherred.dk with new design, chapters and news. | __BY_PARK | Odsherred_progress | 2016-09/2017-03
Producing new leaflet about Geopark Odsherred – 15.000 copies. | __BY_PARK | Odsherred_progress | 2016-09/2017-03
Further progress on the project about the Sun Chariot and where it was found in 1902 in Trundholm Bog. The project was presented in connection with Her Majesty visiting Geopark Odsherred in September 2016. September 2016 – March 2017. | __BY_PARK | Odsherred_progress | 2016-09/2017-03
2 newsletters send to 650 units with the most important news about the activities in Geopark Odsherred. September 2016 – March 2017 | __BY_PARK | Odsherred_progress | 2016-09/2017-03
Further progress and meetings on project about Lammefjord and the local produce (vegetables) involving the local farmers. The National Geological Survey of Denmark and Greenland (GEUS) did complete second round of the geological surveys. The project will finish in 2017. September 2016 – March 2017 | __BY_PARK | Odsherred_progress | 2016-09/2017-03
Preparing new tours for the summer season – bus tours, guided walks, presentations and training programs. September 2016 – March 2017 | __BY_PARK | Odsherred_progress | 2016-09/2017-03
Organizing the 3 day Geopark Festival 2017 (Geopark week) tours and events in the landscape. About 120 different events and 13.000 visitors. September 2017- March 2017 | __BY_PARK | Odsherred_progress | 2016-09/2017-03
Preparing a national network meeting on UNESCO designations in cooperation with the Danish UNESCO National Commission in May 2017. February – March 2017. | __BY_PARK | Odsherred_progress | 2016-09/2017-03
Further progress in the GeoGuide program. 15 new GeoGuides will soon finish the education. September 2016- March 2017 | __BY_PARK | Odsherred_progress | 2016-09/2017-03
Cooperation with University of Copenhagen, Institute for Geoscience and Nature Management. Workshop for 25 international students from Transformation Studio on spatial planning increasingly focuses on the transformation of existing built environments and landscapes through strategic development projects. Focusing on the coastal landscape in Odsherred. February 2017. | __BY_PARK | Odsherred_progress | 2016-09/2017-03
Publishing an article in the European Geoparks Magazine, Issue 13, flagship location Lammefjord, Geopark Odsherred | __NETWORK | Odsherred_progress | 2016-09/2017-03
Participation in the 38th Coordination Committee Meeting in English Reviera UNESCO Global Geopark – September 2016. | __NETWORK | Odsherred_progress | 2016-09/2017-03
Participating in a network meeting in Estonia, October 2016. | __NETWORK | Odsherred_progress | 2016-09/2017-03
Initiating and participating the first Nordic Geoparks Meeting in Reykjanes and Katla Geoparks, Iceland – February 2017 | __NETWORK | Odsherred_progress | 2016-09/2017-03
Participation in the ITB and supporting the EGN-stand. – March 2017 | __NETWORK | Odsherred_progress | 2016-09/2017-03
Further agreements with local partners in Geopark Odsherred. September 2016 – March 2017. | __By_PARTNER | Odsherred_progress | 2016-09/2017-03