## Sheet1
ACTIVITY | TYPE | FILE_NAME | TIME
Production and emplacement of several materials, devices and actions integrated on an overall program of increasing Azores UGG visibility throughout the territory including: i) about 11 new info wood poles in sites of special geological interest in Corvo and Flores islands; ii) improvement of the visibility in the "geoparks corners" in the Azores UGG Island Delegations; | __BY_PARK | Azores_progress | 2017-03/2017-09
Monitoring of the Azores Geopark geosites in cooperation with the Nature Guards from the Natural Parks in all islands, March to September 2017; | __BY_PARK | Azores_progress | 2017-03/2017-09
Publication of the Geopark monthly electronic newsletters and daily update of the Azores Geopark’s facebook, with activities, photos and news, March to September 2017; | __BY_PARK | Azores_progress | 2017-03/2017-09
Production of posters/flyers for on-line dissemination of commemorative dates, in social networks and newsletter; | __BY_PARK | Azores_progress | 2017-03/2017-09
Collaboration with the “Açoriano Oriental” newspaper, by publishing a page every two weeks entitled “(Geo)diversidades”, and the radio station “RDP - Antena 1 Açores”, with the radio program "Geoparque Açores em 5 minutos/Azores Geopark in 5 minutes", twice a week, March to September 2017; | __BY_PARK | Azores_progress | 2017-03/2017-09
Participation in the ITB and BTL tourism fairs, through the Azores Tourism Board, promoting the Azores UGG and the 14th European Geoparks Conference (EGNAZORES2017), March; | __BY_PARK | Azores_progress | 2017-03/2017-09
Development of several activities for the general public, in partnership with the Azores Natural Parks and included in the campaign “Parque Aberto/Open Park”, with a wide diversity of environmental awareness activities, as guided thematic trails in geosites and protected areas and different approaches within the environmental interpretations centres. In all the territory were carried out 76 activities with a total of 3409 participants, March to September; | __BY_PARK | Azores_progress | 2017-03/2017-09
Implementation of the Geopark School Program, integrated in the regional offer “Scholl Park”, with several environmental education activities, for all different education levels. This activity involved schools and students from all islands, and also from the mainland and other countries, during all the scholar year, with 226activities and 6,190 students and teachers, March to September; | __BY_PARK | Azores_progress | 2017-03/2017-09
Development of the exhibition “The Azorean Rocks”, displayed in several partnersestablishments of the Azores Geopark, March to September; | __BY_PARK | Azores_progress | 2017-03/2017-09
Celebration of the 4th anniversary of Azores Geopark with an online contest under the theme “Anniversary of the integration into the EGN”, March; | __BY_PARK | Azores_progress | 2017-03/2017-09
Follow-up of the internship of Sara Rego Vizinho, an Environmental Management student of the Domingos Rebelo High School, whose final work was focused in the Caldeira do Vulcão das Sete Cidades geosite, entitled “Critical Analysis of the Management carried out in the Caldeira do Vulcão das Sete Cidades geosite”, April to June; | __BY_PARK | Azores_progress | 2017-03/2017-09
Organization of the regional event for the “National Olympiads of Geology, 2017”, in the Azores Autonomous Region, involving 24 students in the “regional round”, from 9 schools, and from 7 islands of the archipelago, April; | __BY_PARK | Azores_progress | 2017-03/2017-09
Development of 10 activities integrated in the “Week of the Guide of the Portuguese Geological and Mines Sites Partners”, April 3rdth to 9; | __BY_PARK | Azores_progress | 2017-03/2017-09
Participation in the 2nd Cycle of Sustainable Tourism Sessions, with a presentation titled “Azores UNESCO Global Geopark. A sustainable tourism strategy in 3Gs: Geodiversity, Geconservation and Geotourism”, in Staual th University of Ponta Grossa, Brazil, April 11; | __BY_PARK | Azores_progress | 2017-03/2017-09
Participation and follow up the visit of the EUROPARC to the “Terras do Priolo”, April 19th and 20th; | __BY_PARK | Azores_progress | 2017-03/2017-09
Celebration of the World Earth Day, with 12 activities in the archipelago and 239 nd; participants, April 22 | __BY_PARK | Azores_progress | 2017-03/2017-09
Promotion of two online contest under the theme “Geosites of International Relevance” and “Geoproducts of Azores Geopark” in the Azores Geopark facebook page, April and May; | __BY_PARK | Azores_progress | 2017-03/2017-09
Participation in the Seminar “Sustainable, accessible and inclusive tourism: challenges for Azores destination”, May 8th; | __BY_PARK | Azores_progress | 2017-03/2017-09
Participation in the International Conference “Expor Arte e Património: entre o transitório, o transcendental e o intangível”, with the presentation “Volcanic landscapes of the Azores: Valorization as a natural resource and geological heritage of the Azores Geopark”, May 30th; | __BY_PARK | Azores_progress | 2017-03/2017-09
Promotion of the “2017 European Geoparks Week”, with 23 activities and 562 participants, May 26th to June 11th; | __BY_PARK | Azores_progress | 2017-03/2017-09
Organization and promotion of the activity “Geopaper Entre Montes”, June 3rd; | __BY_PARK | Azores_progress | 2017-03/2017-09
Collaboration in the Field Trip of the 3rd Annual Meeting of the Research group th Centre for Ecology, Evolution and Environmental Changes (cE3c), June 7; | __BY_PARK | Azores_progress | 2017-03/2017-09
Collaboration with the Tourism Office of Maia – “Casa do Povo da Maia”, Association Amigos do Calhau and the Botanic Association of the Azores in the interpretative trail “Fonte Santa/ Praia da Viola”, June 10th; | __BY_PARK | Azores_progress | 2017-03/2017-09
Participation in the event “Rural World Fair”, on Faial Island, with a promotional stand and some activities, June 8th, 9th and 10th; | __BY_PARK | Azores_progress | 2017-03/2017-09
Exhibition of 5 documentaries of the Azores UNESCO Global Geopark on the Azores RTP, July to September; | __BY_PARK | Azores_progress | 2017-03/2017-09
Follow-up of the two evaluators within the Azores Geopark Revalidation Mission, who visited 4 of the 9 islands (São Miguel, Faial, Pico e Terceira), 5th – 9th July; | __BY_PARK | Azores_progress | 2017-03/2017-09
Promotion, with the Environmental Interpretive centre of Caldeira Velha” and the “Urban Skechers Azores”, of the Pico Queimado walking trail, July 23th; | __BY_PARK | Azores_progress | 2017-03/2017-09
Participation in the Regional Meeting of Teachers with the presentation “Geodiversity and geological heritage: the abiotic component of natural heritage” and the workshop “The Azorean Rocks: “putting their hands in the mass””, July 10thth to 13; | __BY_PARK | Azores_progress | 2017-03/2017-09
Participation in the national programme “Ciência Viva no Verão/Alive Science in Summer”, promoted nationally in partnership with the National Network of Science Alive Centres. The Azores Geopark organized 1 activity under the theme “The Rocks of my City” in partnership with stakeholders of the archipelago, with 60 participants, July 22th; | __BY_PARK | Azores_progress | 2017-03/2017-09
Collaboration with the Tourism Office of Maia – “Casa do Povo da Maia” in the interpretative trail “Pedra Queimada-Lajinha-Degredo”, August 19 th | __BY_PARK | Azores_progress | 2017-03/2017-09
Publication of articles for the general public in the “Azorean Spirit” (SATA Inflight Magazine) and one in the special edition in “Visão” about the Azores, August and September; | __BY_PARK | Azores_progress | 2017-03/2017-09
Participation in the 39th EGN CC Meeting on Burren & Cliffs of Moher UNESCO Global Geopark”, in Ennistymon, Irlanda, March 23th e 25th; | __NETWORK | Azores_progress | 2017-03/2017-09
Participation in the 2017 edition of the course "UNESCO Global Geoparks and th th Development of Geotourism", on Lesvos Geopark, Greece, June 12to 22; | __NETWORK | Azores_progress | 2017-03/2017-09
Participation in the project “The journey of Andi Andezit” of Hateg Country Dinosaurs, UNESCO Global Geopark, Romania, July and August; | __NETWORK | Azores_progress | 2017-03/2017-09
Several activities at the aim of the EGN “Volcanic Thematic Working Group”, where the Azores UGG Scientific Coordinator act as Catalyst. | __NETWORK | Azores_progress | 2017-03/2017-09
The Azores Geopark has currently about 45 partners, including public and private institutions and private companies. For a detailed listing and characterization of the partners activities consider checking the Azores Geopark Newsletters. | __By_PARTNER | Azores_progress | 2017-03/2017-09