## Sheet1
ACTIVITY | TYPE | FILE_NAME | TIME
Following action plan relevant to Recommendations for revalidation 2017. | __BY_PARK | Katla_progress | 2015-09/2016-03
Numerous articles on Katla UNESCO Global Geopark in national newspapers. | __BY_PARK | Katla_progress | 2015-09/2016-03
Ongoing work on Communication plan, criteria and guidelines for the use of EGN and our Geopark logo and Contracts for partners. September – January. | __BY_PARK | Katla_progress | 2015-09/2016-03
Talks at the assembly of Municipality board of Skaftárhreppur and Rangárþing eystra about Katla Geopark and UNESCO. Talks on the benefit of the Geopark for local enterprises and contracts for use of logo, meetings with enterprise- clusters. Talks and meetings on education in Katla Geopark Oct-Feb. | __BY_PARK | Katla_progress | 2015-09/2016-03
Correspondence for scientific collaboration between the Icelandic Met Office, Geological survey of University of Iceland, bird survey of south Iceland, Fisheries and other highly relevant institutes for geo-education. Sept-Feb. | __BY_PARK | Katla_progress | 2015-09/2016-03
Collaboration of Uni, of Iceland, Skaft. Municipality, NOHINK-design Holland, Katla Geopark and V. Nat Park input for Management plan. Nov2015/Feb 2016. | __BY_PARK | Katla_progress | 2015-09/2016-03
Private meeting with Prime Minister of Iceland and Representatives of Katla Geopark. Introduction to UNESCO Global Geoparks, the extent of Public lands (þjóðlendur) within the Geopark and the need of funding for the employment required by UNESCO for the running of tha Geopark. Reykjavík December 2015. | __BY_PARK | Katla_progress | 2015-09/2016-03
Establishment of cooperation for app-based educational trails within Katla Geopark with “Wapp” (walk-app). December 2015. | __BY_PARK | Katla_progress | 2015-09/2016-03
Geo Education. Initiation of GeoSchool project with grant from ministry of Education and meetings with headmasters and lead teachers of the three schools. Cooperation with UNESCO school project in Reykjavík. Submission of grant for making of GeoEducational material. September- February, ongoing. | __BY_PARK | Katla_progress | 2015-09/2016-03
Participation in the 13th European Geoparks Conference hosted in Rokua Geopark – Finland 3-6 September 2015. | __NETWORK | Katla_progress | 2015-09/2016-03
Participating in the 8th International ProGeo Symposium, Reykjavík – Iceland, and co-hosting the 8th two day trip around the south, Katla Geopark 8-12 Sept. | __NETWORK | Katla_progress | 2015-09/2016-03
Collaboration and interactive public meetings for protection and awareness of intangible heritage in Katla Geopark. UNESCO, September-January 2015-2016. | __NETWORK | Katla_progress | 2015-09/2016-03
Meetings with Ministry of Environment, Cultural Heritage Agency, Planning agency for better cooperation and signage. | __NETWORK | Katla_progress | 2015-09/2016-03
Work with Prime Minister’s Office and Municipalities in Iceland about the making of ownership plan for Common lands (i.Þjóðlendur) and future cooperation. | __NETWORK | Katla_progress | 2015-09/2016-03
Correspondence with President´s office for Publication of UNESCO press release on the visit of Iceland and France presidents to Katla Geopark Geosite Sólheimajökull global warming evidence. | __NETWORK | Katla_progress | 2015-09/2016-03
Attending of the Prime Minister visit and Public meeting for assessment of damage and cause following largest glacial outburst in river Skaftá. October 2015 | __NETWORK | Katla_progress | 2015-09/2016-03
Planning of Exhibition hall on new GeoExhibition, GeoSaga, Kötlusetur, Vík and Lava centre Hvolsvöllur. Visibility and GeoEducation on Katla Geopark. | __NETWORK | Katla_progress | 2015-09/2016-03
Ongoing work, laying out roles and future plans with Marketing office of South Iceland. Official Marketing body of Katla Geopark. November – February. | __NETWORK | Katla_progress | 2015-09/2016-03
Grant application and receiving from NORA, in collaboration with Magma Geopark of Norway, for enhancement of virtual educational interpretation of geological heritage for visitor centre. October 2015. | __NETWORK | Katla_progress | 2015-09/2016-03
Erasmus+ GeoEducation, Hosting of Teachers and Trainers seminar Katla Geopark 7-11 October 2015. Majors from Katla Geopark Visiting Arouca Geopark, Portugal. Nov. 2015. Participating in the NPP - Drifting Apart project, second meeting of seven countries, Reykjanes Geopark. December 2015. | __NETWORK | Katla_progress | 2015-09/2016-03
Reinforcement of collaboration and visibility between Katla Geopark and Vatnajökull National Park. October-February. | __NETWORK | Katla_progress | 2015-09/2016-03
GeoSecurity. Colaboration with Police of South Iceland for security measures and cooperation with Finish partners, NPA grant application. Ongoing. Police patrol in Reynisfjara due to high tide and frequent mishaps of tourists, one fatality. Ongoing work for better security measures due to tourists not taking heed of warning signs. | __NETWORK | Katla_progress | 2015-09/2016-03
Collaboration with new Tourist Management Agent of Iceland. | __NETWORK | Katla_progress | 2015-09/2016-03
Grants: Nora (Des) granted for making 3D filming, grant for GeoSchools and Protection. Application of grant for better signage of and in Katla and producing educational material, awaiting. | __NETWORK | Katla_progress | 2015-09/2016-03
UNESCO Heritage site preparation on our doorstep, Friðland að Fjallabaki. | __By_PARTNER | Katla_progress | 2015-09/2016-03
Publication of an illustrated colouring book on Folk Stories from around Vík. | __By_PARTNER | Katla_progress | 2015-09/2016-03
Saga Geopark project. Admission of application to UNESCO Global Geoparks, December | __By_PARTNER | Katla_progress | 2015-09/2016-03
Inauguration of publication of book “Brunasandur”, December. | __By_PARTNER | Katla_progress | 2015-09/2016-03
Heritage agency reconstructing Steinahellir & Rútshellir, with communal signage. | __By_PARTNER | Katla_progress | 2015-09/2016-03