## Sheet1
ACTIVITY | TYPE | FILE_NAME | TIME
Geoloday (Free guided geo-route organized at national level, 290 participants in our two provinces) May 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Artistic intervention-perform in an abandoned village (30 participants) -May 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
EGN Week: talks and geo-tours (235 participants) -May-June 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Many interviews and articles of the Geopark in local, regional and national media, also radio and TV- May-September 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Oral presentation in the Natural history museum of Burgos and in Sobrarbe Geopark- May 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Meetings with Aguilar and Villadiego mayors for work in the future Reception centres of the Geopark-May-June 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Meetings with the regional government and councils for prepare the collaboration agreements for 2017-2018 and the Road sing Plan-June-July 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Co-author in a poster for the XII National Meeting of Geological Heritage Commission of the Geological Society of Spain – June 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Meetings with the Caja de Burgos Foundation for collaboration agreements for a research and student program-June 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Volunteering program: Scientific study in Las Loras Geopark: Inventory and characterization of vulnerable areas: peatlands and calcareous tuffs of Las Loras Geopark. Proposals for monitoring and custody - June-September 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Field trips with the technicians of the regional government and of the Natural protected areas of Covalagua for re-design and create new routes and panelling related to the Geopark and for create a protocol for the protection of geological heritage-May-August 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Presentation of the Geopark in surrounding cities outside of the Geopark-June- August 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Meetings for the preparation and launch of the tourism product (geo-guided tours) with the geopark team and the guides-July 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Field trips and preparation of information materials with the students of the Secondary School of Villadiego of the Erasmus plus Program, of exchange of students between European geoparks- May-June 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Guided geo-routes for the different Cultural and Research associations of the territory and local and regional government- May-August 2017 | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Editing the new leaflet and map of the Geopark and distributing them in the touristic information offices. | __BY_PARK | Las_Loras_progress | 2017-03/2017-09
Participation in the presentation of the European Geopark week in the Spanish Geological Survey in Madrid, May 2017 | __NETWORK | Las_Loras_progress | 2017-03/2017-09
Participation in the meeting of the Spanish National Committee of Geoparks, June 2017 | __NETWORK | Las_Loras_progress | 2017-03/2017-09
Write an article for the GGN newsletter- August 2017 | __NETWORK | Las_Loras_progress | 2017-03/2017-09
Organisation and promotion of the EGN Week- May–June 2017 | __NETWORK | Las_Loras_progress | 2017-03/2017-09
Helping the Aspiring Saimaa Geopark, Finland (sending them information and documents about our Geopark, dossier, annexes, self-evaluation doc, etc.) | __NETWORK | Las_Loras_progress | 2017-03/2017-09
Beginning of the works in the building for the Reception Geopark Centre in Villadiego by the village and regional Council- June 2017 | __By_PARTNER | Las_Loras_progress | 2017-03/2017-09
Beginning of the clearing and settlement works on the routes of the Geopark by the Regional government forest work crew- July 2017 | __By_PARTNER | Las_Loras_progress | 2017-03/2017-09
Week of the Erasmus plus program in the Secondary School of Villadiego- Collaborate in the different activities and workshops-June 2017 | __By_PARTNER | Las_Loras_progress | 2017-03/2017-09
Participation and help at the First Festival of Short Films in Villadiego (with special mention for those filmed in the Geopark)-August 2017 | __By_PARTNER | Las_Loras_progress | 2017-03/2017-09
Helping and collaborating in the Preview of the film "With the wind" shot in the Geopark (Outdoor projection with more than 600 people from the people of las Loras villages, impressive and emotional for the older people)- August 2017 | __By_PARTNER | Las_Loras_progress | 2017-03/2017-09
Inaugurated a new historical trail on the Civil War by the Sargentes de la Lora council (Burgos) with the collaboration of the Geopark-August 2017 | __By_PARTNER | Las_Loras_progress | 2017-03/2017-09