## Sheet1
ACTIVITY | TYPE | FILE_NAME | TIME
September 2014 – Geopark Odsherred admission in the EGN / GGN as the first Geopark in Denmark. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Celebrating the admission Global Geopark Odsherred with the local inhabitants of Odsherred Municipality, October 2014. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Numerous interviews and articles on the admission of Geopark Odsherred in the national and regional media, September – October 2014. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Closure of the process of trademark protection regarding the Geopark Odsherred logo, October 2014. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Visit from Estonia, 30 participants from the Jõgevamaa Koostöökoda-area wanting to hear about how to make a Geopark, October 2014. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Guided geotours with altogether more than 500 participants, September-October 2014. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Extending and further development of the smart phone app The Landscape Created by the Ice to be finished in spring 2015, September - December 2014. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Working with two schools (250 pupils) in the Geokids project giving outdoor class lessons about the geology and landscape, cultural history, art and local produce in Geopark Odsherred and finally making their own Geokids mask, October- November 2014. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Organizing the final elements in creating a new “Ridge Path” across the end moraines in Geopark Osherred together with the local stakeholders. The Ridge Path will be ready for inauguration in summer 201,. January-March 2015. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
New Geopark organization from January 1st 2015 Geopark Odsherred was secreted from the Odsherred Municipality and the Geopark Odsherred Foundation was established. January – March 2015. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Coauther on a Special Edition of the magazine “Geoviden no. 1, 2015” from the National Danish Geological Survey on Geopark Odsherred, January 2015. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Promoting Geopark Odsherred in Holiday Partner magazine for holiday rental houses, February 2015 | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Promoting Geopark Odsherred in tourist magazine for the local Tourist Bureau Visit Odsherred, February 2015. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Promoting Geopark Odsherred in the local magazine “Landliggeren” for the 25.000 holiday house owners within the Geopark. The magazine is distributed to all households, March 2015. | __BY_PARK | Odsherred_progress | 2014-09/2015-03
Authoring an article for the European Geoparks Magazine 2015, October 2014. | __NETWORK | Odsherred_progress | 2014-09/2015-03
Participation in the 35th European Geoparks Network Coordination Committee meeting in Paris, March 2015. | __NETWORK | Odsherred_progress | 2014-09/2015-03
Participation in the Nordic GEOfood-project with Magma and Rokua Geoparks, September 2014-March 2015. | __NETWORK | Odsherred_progress | 2014-09/2015-03
Meeting with all potential partners (120 participants) in the Geopark-area discussing themes for the new 4-year-strategy for Geopark Odsherred, November 2014. | __By_PARTNER | Odsherred_progress | 2014-09/2015-03
Developing partnership agreements between Geopark Odsherred and local businesses and public institutions on how to participate in the Geopark developing work and how to use the Geopark-logo, January - March 2015. | __By_PARTNER | Odsherred_progress | 2014-09/2015-03
Developing partnership agreements with local farmers developing a Geopark- brand for their local produce. Also developing partnership agreements with local restaurants getting them to make menus and dishes with at least 50 % local produce – kind of GEOfood-dish, September 2014-march 2015. | __By_PARTNER | Odsherred_progress | 2014-09/2015-03