## Sheet1
ACTIVITY | TYPE | FILE_NAME | TIME
The new masterplan is on its way. A working group is established. The website invites local people to participate. Three thematic workshops dealt with issues like general analysis, sustainable tourism, regional development, education, communication, natural assets and landscapes. Two more workshops are coming up in autumn. Final results will be presented in spring 2015. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
In April Timo offered two information sessions for new tourguides for the new Silverlake gallery. 18 Guides have been trained and are now able to inform about geology, fauna and flora, mining history and safety regulations . The official opening took place at the 24th of April and 230 guests were able to experience the new attraction. Meanwhile 1.500 visitors booked a guided tour. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
Two new printed hiking guides are available in regional bookstores, one of them covering all local trails in the southern Geopark and another giving guidance on a long distance trail (about 100 km) on the ridge of the Wiehenmountains. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
The first 4 day Geopark Expedition took place during the European Geoparks week from 29th of May and 1st of June. Organized by TERRA.vita and Geopark De Hondsrug in the Netherlands 3 families from each Geopark competed and enjoyed the highlights of both parks. The winner family from NL received a complete family weekend in a hotel in TERRA.vita and the first family from Germany a weekend in De Hondsrug. The plan is to establish this event as a bookable annual package for a tour operator. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
The staff of the TERRA.vita info center in Osnabrück got a refreshing training on new TERRA.vita issues and perspectives. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
The new TERRA.ticket, offering a special rate for people visiting the central Geopark by public transport was presented to the press together with 30 mayors. It is planned to extend the range to other more remote areas in the park. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
At 1st of July TERRA.vita recruited two fulltime employees. Sabine Böhme (background tourism management) will be working on partnership initiatives, regional products and extension of the TERRA.ticket. Michael Hein (background regional management and forestry) will improve and reconstruct the Geoparks hiking trail system and establish a quality management. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
A group of 6 students from the University of Applied Sciences in Osnabrück started a semester project on regional products in the Geopark. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
Student Jannik Müller develops during a half year internship, financed by Commerzbank, a concept for mountainbiking network and routes in the Geopark. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
The model of the TERRA.vita E-Bike recharging station has been exported for the first time to the neighbouring Naturepark “Dümmer”. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
During the first half year, one of the mayor attractions of the geopark, the vista point on the Piesberg mountain was visited by nearly 20.000 people. The data was collected by our eco counter. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
A permanent contact has been developed to our Member of Parliament Mrs. Anja Karlizcek. She will organize a meeting with other MP`s from other German GGN parks in autumn in Berlin. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
All letters which have been sent out by the German Geopark Forum (in this case the county manager of Osnabrück and the president of TERRA.vita) aiming to add more persons and important organisations have been answered. The ministry of the environment is not interested to join the Forum. All others, the Federal Ministries of Economics and Exterior, the German UNESCO Commission, the German Environment Foundation and the Alfred Wegener Foundation expressed their interest to collaborate, depending on progress in Paris on the UNESCO Geopark issue. | __BY_PARK | TERRA_vita_progress | 2014-03/2014-09
Timo and Hartmut were partners in two revalidation missions, one to Rokua Geopark (FIN) and one to The Bohemian Paradise (CZ). | __NETWORK | TERRA_vita_progress | 2014-03/2014-09
Our 4 partner counties and 2 big partner cities have been asked to collect data on how much time their staff is working on TERRA.vita issues. Altogether officially we can add (indicated by name) a working power of an equivalent of two more people to our staff. Contact : | __By_PARTNER | TERRA_vita_progress | 2014-03/2014-09